## Sheet2
Month : Febuary/2019 | [7 empty] | Progress Colors
DATE-WISE LIST OF ACTIVITIES COMPLETED/IN PROGRESS/SCHEDULED
| date | Activity names and progress colors below per day
| 1 | form for registered jobseeker applying for job | notification for update of profile data | applied jbsekr database tables desing | jobs applying & already applied showing | linking index and dashboard | apply easy apply tags on jobs | Scheduled
| 2 | form for registered jobseeker applying for job | manytomanytable between jobs nd jobseeker | applied jbsekr database tables desing | jobs applying & already applied showing | linking index and dashboard | apply easy apply tags on jobs
| 3 | form for registered jobseeker applying for job | manytomanytable between jobs nd jobseeker | applied jbsekr database tables desing | jobs applying & already applied showing | linking index and dashboard | apply easy apply tags on jobs
| 4 | forgot paasword for user | navbar homepage link design jobseeker | applied jbsekr database tables desing | jobs applying & already applied showing | making navbar of azam-st | designing animation for slider
| 5 | forgot paasword for user | navbar homepage link design jobseeker | https www redirection | azam-st design help abdul waheed | making navbar of azam-st | designing animation for slider
| 6 | Saturday/Sunday
7
| 8 | forgot paasword for user | navbar homepage link design jobseeker | https www redirection | making the azam-stproject available on git | deploying enviroment for group working
| 9 | forgot paasword for user | file upload javascript validation for jobseeker | https www redirection | making the azam-stproject available on git | deploying enviroment for group working |  | in Progress
| 10 | forgot paasword for user | file upload javascript validation for jobseeker | https www redirection | making the azam-stproject available on git | deploying enviroment for group working
| 11 | forgot paasword for user | file upload javascript validation for jobseeker
12
| 13 | Saturday/Sunday
14
15
16
17
| 18 | [6 empty] | completed
19
| 20 | Saturday/Sunday
21
22
23
24
25
26
| 27 | Saturday/Sunday
28
29
30
31