## srs rizqdoor
No | Priority | Complexity | Requirements | Status
1 | High | Low | Careers Page
5 | High | Low | Dashboard Design Responsiveness Correctness
2 | High | Medium | Statistics of jobseeker
3 | High | Medium | Statistics of Employer
6 | High | Medium | Show recent Searches Based on cookies when someone visits
7 | High | Medium | subscription through linked accounts show subscription lists
4 | High | Very High | Searching Search Filters and Results design
8 | Medium | High | Push Notification from browser
13 | Medium | medium | A complete profile of jobseeker E.G Rozee.pk
14 | Medium | medium | Search jobseeker option for employer
9 | Medium | Very High | Login With Facebook and linkedin
10 | Medium | Very High | Crawl other jobs portals for jobs in index page E.G indeed
11 | Medium | Very High | Cv Builder for profile
12 | Medium | Very High | Company Own Dashboard and website analytics
16 | Low | high | Advertise with us page
18 | Low | high | online chat system for help
15 | Low | low | show loader when loading the page E.G Youtube
17 | Low | low | Community Services
19 | Low | merdium | counter increment of country and industory when first time website loads

## March19
Month : Febuary/2019 | [7 empty] | Progress Colors
DATE-WISE LIST OF ACTIVITIES COMPLETED/IN PROGRESS/SCHEDULED
| date | Activity names and progress colors below per day
| 1 | dashboard desing | designing update form | Main menu designing | Side bar designing | user profile photo UI design | Update form design | Scheduled
| 2 | Saturday/Sunday
3
| 4 | main menu design | designing update form | side bar design | update form constraints | backend coding for profile pic | database entity for pic
| 5 | update form constraints | backend coding for profile pic jobseker | user sign out option | user cv upload form jobseker | database entity for pic | backend file system and coding for cv
| 6 | jobseeker password update form | backend coding for profile pic jobseker | employer password update form | user cv upload form jobseker | emp password form backend | jobseeker password form backend
| 7 | jobseeker password update form | backend coding for profile pic jobseker | employer password update form | user cv upload form jobseker | emp password form backend | jobseeker password form backend
| 8 | user sign out option | backend coding for profile pic jobseker | statistics design for emp | user cv upload form jobseker | statistics design for jobseeker | delete account for emp and jobseeker
| 9 | Saturday/Sunday | [5 empty] | in Progress
10
| 11 | navbar homepage link design emp | azam-st.com japanese hack issue | statistics design for emp | change user cv option jobseeker | statistics design for jobseeker | delete account for emp and jobseeker
| 12 | navbar homepage link design emp | azam-st.com japanese hack issue | statistics design for emp | change user cv option jobseeker | statistics design for jobseeker | delete account for emp and jobseeker
| 13 | navbar homepage link design emp | azam-st.com japanese hack issue | statistics design for emp | change user cv option jobseeker | statistics design for jobseeker | delete account for emp and jobseeker
| 14 | form uploading datatype solved | form not showing text error solved | statistics design for emp | change user cv option jobseeker | statistics design for jobseeker | userjobseeker form animation
| 15 | form uploading datatype solved | form not showing text error solved | statistics design for emp | account creation date in db jobseker | statistics design for jobseeker | userjobseeker form animation
| 16 | Saturday/Sunday
17
| 18 | heading capitalized not showed | form not showing text error solved | account creation date in db jobseker | account creation date in db jobseker | creation date in every table | userjobseeker form animation | completed
| 19 | heading capitalized not showed | form not showing text error solved | account creation date in db jobseker | account creation date in db jobseker | creation date in every table | userjobseeker form animation
| 20 | file upload javascript validation for employer | form not showing text error solved | account creation date in db jobseker | account creation date in db jobseker | creation date in every table | constraints on redirection for loged jobseeker
| 21 | file upload javascript validation for employer |  | account creation date in db jobseker | account creation date in db jobseker | creation date in every table | constraints on redirection for loged jobseeker
| 22 | file upload javascript validation for employer | Profile image design jobseeker | profile image update form | profile image new upload form | creation date in every table | constraints on redirection for loged jobseeker
| 23 | Saturday/Sunday
24
| 25 | file upload javascript validation for employer | Profile image design jobseeker | profile image update form | profile image new upload form | making new index for logd user | designing alert box of javascript
| 26 | notification for updation of picture | Profile image design jobseeker | profile image update form | profile image new upload form | making new index for logd user | designing alert box of javascript
| 27 | notification for updation of picture | Profile image design jobseeker | profile image update form | profile image new upload form | making new index for logd user | designing alert box of javascript
| 28 | notification for updation of picture | notification for update of profile data | notification for login success | login showing on homepage | making new index for logd user | applying as a logged in jobseker
| 29 | notification for updation of picture | notification for update of profile data | notification for login success | login showing on homepage | making new index for logd user | applying as a logged in jobseker
| 30 |  | notification for update of profile data | notification for login success | login showing on homepage | making new index for logd user | applying as a logged in jobseker
| 31 | Saturday/Sunday

## April19
Month : Febuary/2019 | [7 empty] | Progress Colors
DATE-WISE LIST OF ACTIVITIES COMPLETED/IN PROGRESS/SCHEDULED
| date | Activity names and progress colors below per day
| 1 | form for registered jobseeker applying for job | notification for update of profile data | applied jbsekr database tables desing | jobs applying & already applied showing | linking index and dashboard | apply easy apply tags on jobs | Scheduled
| 2 | form for registered jobseeker applying for job | manytomanytable between jobs nd jobseeker | applied jbsekr database tables desing | jobs applying & already applied showing | linking index and dashboard | apply easy apply tags on jobs
| 3 | form for registered jobseeker applying for job | manytomanytable between jobs nd jobseeker | applied jbsekr database tables desing | jobs applying & already applied showing | linking index and dashboard | apply easy apply tags on jobs
| 4 | forgot paasword for user | navbar homepage link design jobseeker | applied jbsekr database tables desing | jobs applying & already applied showing | making navbar of azam-st | designing animation for slider
| 5 | forgot paasword for user | navbar homepage link design jobseeker | https www redirection | azam-st design help abdul waheed | making navbar of azam-st | designing animation for slider
| 6 | Saturday/Sunday
7
| 8 | forgot paasword for user | navbar homepage link design jobseeker | https www redirection | making the azam-stproject available on git | deploying enviroment for group working
| 9 | forgot paasword for user | file upload javascript validation for jobseeker | https www redirection | making the azam-stproject available on git | deploying enviroment for group working |  | in Progress
| 10 | forgot paasword for user | file upload javascript validation for jobseeker | https www redirection | making the azam-stproject available on git | deploying enviroment for group working
| 11 | forgot paasword for user | file upload javascript validation for jobseeker
12
| 13 | Saturday/Sunday
14
15
16
17
| 18 | [6 empty] | completed
19
| 20 | Saturday/Sunday
21
22
23
24
25
26
| 27 | Saturday/Sunday
28
29
30
31